## 1. Risk Register Template
(ORGANIZATION NAME) |  | XYZ
This risk assessment is aligns with: |  |  | ISO 27001
Objective: |  |  | Risk Assessment (Risk Register)
Date of the risk assessment: |  |  | 14/4/2024
Version |  |  | 1
Risk should be reassessed periodically throughout the life of the program or project.
Document Author |  |  | Ali Abdelhamid
Author Job Title |  |  | Student
Approved by |  |  | Islam Fathy
Approver Job Title |  |  | Dr
This risk assessment is aligns with: |  | CONTEXT (For Guidance, See Tab 3) | RISK IDENTIFICATION |  |  |  | ANALYSIS Residual risk rating with treatments in place (For Guidance, See Tab 4) |  |  |  | EVALUATION (For Guidance, See Tab 5) |  |  | TREATMENT MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all treatments, including additional treatments, are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of treatments implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Risk tolerance executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned treatments, and associated costs.)
RISK # | CATEGORY | BUSINESS OBJECTIVE/ PRIORITY | RISK EVENT | RISK CAUSE | IMPACT | CURRENT TREATMENTS | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | ADEQUACY OF CURRENT TREATMENTS | ACTION | TREND | ADDITIONAL PLANNED TREATMENT | DELIVERABLES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | STATUS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP
Add identifiers to better organize and track risks. | Which category does this Risk Event fall under? | What business objective/priority does this Risk Event affect (e.g., Mandate letter, strategic directive, etc.)? | What events could impact the achievement of objectives (can be positive or negative)? | What Risk Cause (trigger, circumstance, uncertainty) could increase the Likelihood of the Risk Event occurring? There are usually multiple Risk Causes leading to a Risk Event. | How would the Risk Event impact the achievement of the objective/priority? | What Treatments are currently in place to manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | How likely? | How severe? | (LxC) | Rating with current treatments in place | Non-existent Inadequate Adequate Robust | Will you do more to manage the risk (treat) or choose to accept and monitor? | If applicable, has this risk rating changed over time? Has column J increased (upward trend), decreased (downward trend) or not changed (static) | What Treatments are needed to further manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | Future Treatments will come in what form (e.g., a project plan, a briefing note, report, funding request, other)? | Who will take the lead on this mitigation? | When should the deliverable be ready? (Optional) | Do the Risk Event or Treatments depend on another team or organization? Do they impact another group? | On Track Slowed Stalled |  |  |  |  | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place
1 | Cybersecurity | data integrety | Data Breach due to Phishing | Phishing Email | Major disruption to financial services | Email filters, Employee Training | 4 | 4 | 16 | HIGH | Inadequate | Review and enhance phishing detection and response strategies | Upward, indicating an increase in phishing attempts | Advanced phishing detection system implementation | System Upgrade Plan | CISO | Q3 2024 | Coordination with IT Department for system integration | On Track | 25% | Increased sophistication of phishing attacks observed; ongoing monitoring and update of filters required | Deploy new system and conduct follow-up training | Q4 2024 | 3 | 3 | 9 | MEDIUM | 4 | 4 | 16 | HIGH | 3 | 3 | 9 | MEDIUM
2 | Technical | System Availability | Outdated Software Vulnerability | Lack of regular updates | System downtime with operational repercussions | Scheduled updates, Patch management system | 3 | 3 | 9 | MEDIUM | Adequate | Implement automated patch management and regular security audits | Static, as recent security patches have been consistent | Automated patch management system | Automated Patch Management Implementation Plan | IT Manager | Q2 2024 | Coordination with software vendors for timely patch releases | On Track | 50% | Dependency on vendor response time for patch availability | Accelerate deployment of automated patching; re-assess patching strategy | Q1 2025 | 2 | 2 | 4 | LOW | 3 | 3 | 9 | MEDIUM | 3 | 2 | 6 | MEDIUM
3 | Compliance | Adherence to Financial Regulations | Regulatory Non-Compliance | Inadequate understanding of new regulations | Fines and legal repercussions, loss of customer trust | Regular compliance training, updates from legal team | 2 | 4 | 8 | MEDIUM | Adequate | Develop a compliance update system, enhance legal team engagement | Downward, improvements seen with recent training initiatives | Compliance management software implementation | Compliance Software Roll-out Plan | Chief Compliance Officer | Q4 2024 | Coordination with regulatory bodies and internal departments | In Progress | 30% | Increasing complexity of financial regulations requires enhanced training | Continuous compliance monitoring and education | Q2 2025 | 1 | 3 | 3 | LOW | 2 | 4 | 8 | MEDIUM | 2 | 3 | 6 | MEDIUM
4 | Operational | Business Continuity | IT System Downtime | Hardware Failure | Disruption to core business operations and customer service | Redundant system architecture, regular hardware maintenance | 2 | 4 | 8 | MEDIUM | Adequate | Upgrade hardware to more reliable technology, implement real-time monitoring systems | Static, as hardware upgrades have recently been implemented | Disaster recovery plan enhancement | Updated Disaster Recovery Plan | Chief Technology Officer | Q1 2024 | Coordination with IT department and hardware vendors | In Progress | 40% | Some legacy hardware may still be in use; budget for new hardware needed | Complete the phase-out of legacy hardware, conduct disaster recovery drills | Q3 2024 | 1 | 3 | 3 | LOW | 2 | 4 | 8 | MEDIUM | 2 | 2 | 4 | LOW
5 | Cybersecurity | Network Security Enhancement | Security Breach due to Advanced Persistent Threats (APT) | Sophisticated Cyber-attacks | Potential data loss, operational disruption, reputational damage | Firewall upgrades, intrusion detection systems (IDS), staff cybersecurity training | 3 | 4 | 12 | HIGH | Inadequate | Implement advanced threat hunting, enhance SIEM (Security Information and Event Management) capabilities | Static, despite increasing APT sophistication | Deploy advanced network security infrastructure, conduct red team exercises | Advanced Network Security Plan, Red Team Exercise Report | CISO | Q2 2025 | Collaboration with cybersecurity vendors and internal IT teams | In Progress | 35% | Need to address emerging threats proactively, improve threat intelligence | Continuous security monitoring, frequent penetration testing | Q4 2025 | 2 | 3 | 6 | MEDIUM | 3 | 4 | 12 | HIGH | 2 | 2 | 4 | LOW
6 | Legal | Compliance with GDPR | Data Privacy Breach | Inadequate Data Protection Measures | Legal fines, loss of customer trust, reputational damage | GDPR training for staff, data encryption, privacy policy updates | 3 | 5 | 15 | HIGH | Inadequate | Enhance data protection protocols, conduct regular GDPR audits | Downward, as recent GDPR training has increased awareness | Implementation of a Data Protection Officer role, regular compliance audits | GDPR Compliance Enhancement Plan | Compliance Officer | Q4 2024 | Coordination with the legal department, IT security team | In Progress | 60% | Ongoing adjustments to data handling processes required | GDPR refresher courses | Q2 2025 | 2 | 3 | 6 | MEDIUM | 3 | 5 | 15 | HIGH | 1 | 2 | 2 | LOW
7 | Cybersecurity | Protect Intellectual Property | Theft of Sensitive Technology Data | Cyber Espionage | Loss of competitive edge, intellectual property theft | Advanced network monitoring, AI-based anomaly detection, strict access controls | 2 | 5 | 10 | MEDIUM | Adequate | Strengthen end-point security, enhance threat intelligence capabilities | Static, with no recent incidents following the latest security upgrades | Zero Trust security implementation, employee security awareness program | Zero Trust Framework Implementation, Security Awareness Training Schedule | CISO | Q3 2024 | Collaboration with R&D and IT departments | In Progress | 40% | Increasing sophistication of cyber-attacks targeting tech industries | Regular security audits, cybersecurity drills, update incident response plan | Q2 2025 | 1 | 3 | 3 | LOW | 2 | 5 | 10 | MEDIUM | 1 | 2 | 2 | LOW
8 | Cybersecurity | Secure Customer Data | Unauthorized Access to Customer Information | Insufficient Access Controls | Data breach, legal penalties, erosion of customer trust | Two-factor authentication, regular access audits, employee access control training | 2 | 5 | 10 | MEDIUM | Adequate | Upgrade to multi-factor authentication, enhance user behavior analytics | Static, with no incidents since the last audit | Comprehensive access control review, implementation of least privilege policy | Access Control Enhancement Plan, User Privilege Audit Report | Data Protection Officer | Q1 2025 | Coordination with IT security and HR departments | In Progress | 45% | Rising trend in targeted phishing attacks requires more robust controls | Introduce biometric authentication, continuous security awareness campaigns | Q3 2025 | 1 | 3 | 3 | LOW | 2 | 5 | 10 | MEDIUM | 1 | 2 | 2 | LOW
9 | Information Technology | Maintain IT Infrastructure Integrity | Network Infrastructure Failure | Aging Hardware or Software Failure | Service disruption, operational delays, customer dissatisfaction | Regular maintenance schedule, network performance monitoring | 2 | 4 | 8 | MEDIUM | Adequate | Plan hardware and software upgrades, increase redundancy | Downward, following recent infrastructure investments | IT infrastructure overhaul, enhanced disaster recovery planning | Infrastructure Upgrade Project Plan, Disaster Recovery Protocol | IT Director | Q3 2024 | Coordination with external IT service providers, alignment with business continuity planning | In Progress | 60% | Budget constraints impacting upgrade timeline | Secure additional funding, prioritize critical infrastructure upgrades | Q2 2025 | 1 | 2 | 2 | LOW | 2 | 4 | 8 | MEDIUM | 2 | 4 | 8 | MEDIUM
10 | Technology | System Uptime and Reliability | Cloud Service Downtime | Overload or Distributed Denial of Service (DDoS) Attack | Inability to access critical applications, loss of productivity, customer service impact | Load balancing, DDoS protection services, cloud resource scaling | 2 | 4 | 8 | MEDIUM | Adequate | Implement enhanced cloud security measures, review service level agreements (SLAs) | Static, as current measures have been effectively preventing known attack patterns | Cloud security posture assessment, increased bandwidth provision | Cloud Security Enhancement Strategy, SLA Review Document | Cloud Services Manager | Q4 2024 | Cloud service provider cooperation, IT security team alignment | In Progress | 50% | Evolving threat landscape requires a dynamic response strategy | Continuous monitoring, security incident drills, and response plan updates | Q1 2025 | 1 | 3 | 3 | LOW | 2 | 4 | 8 | MEDIUM | 2 | 2 | 4 | LOW

## 2. Process Help
RISK MANAGEMENT PROCESS: OVERVIEW
1. The SCOPE, CONTEXT, and CRITERIA identifies the subject of the risk assessment. For Guidance, See Tab 3.
2. IDENTIFY risks by asking, "What could occur that would have an impact on our objectives?" Risks have three key elements: Event, causes, impacts.
3. Risks ANALYSIS involves ranking the likelihood and consequence using a 1-5 scale. For Guidance, See Tab 4.
4. In order to EVALUATE risks the group reviews the effectiveness and appropriateness of currents controls and determines what action to take, if any. For Guidance, See Tab 5.
5. Risk TREATMENT is the activity (s) you are going to implement to better manage your exposures. Your mitigations will reduce the likelihood and/or consequence of the risk event occurring.
for more information, please see the Risk Management Guideline for the B.C. Public Sector.

## 3. Assessment Context
CONTEXT TEMPLATE
ESTABLISH CONTEXT: The first step in any risk assessment is to set the context. Use this optional template to establish scope, criteria, and deliverable for your organization. Refer to your organizations's Mandate Letter, Service Plan, and other strategic initiatives.
1. State the Business Objectives/Priorities of your organization.
Text text text.
2. State the mission, vision, operating principles and any other value criteria.
Text text text.
3. Identify stakeholders; determine their influence on the organizations's objecitves, methods of consultation and communciation, as appropriate.
Text text text.
4. Set out assumptions and constraints (deadlines, time-frames, environmental factors, or executive directives).
Text text text.

## 4. L&C Matrix
RISK RATING MATRIX (LIKELIHOOD AND CONSEQUENCE)
Likelihood and Consequence Descriptors for Risk Assessments
Likelihood | Rating | Criteria | Probability
Almost certain | 5 | It is expected to happen. Will certainly happen this fiscal year or during the three year period of the Service Plan. | 80% to 100% or once a year or more frequently
Likely | 4 | We expect it to happen. It would be surprising if this did not happen. | 61% to 79% or once every 3 yrs
Possible | 3 | Just as likely to happen as not. We don't expect it to happen, but there is a chance. | 40% to 60% or once every 5 yrs
Unlikely | 2 | Not anticipated. We won't worry about it happening. | 11% to 39% or once every 15 years
Almost certain not to happen | 1 | It would be surprising if this happened. There would have to be a combination of unlikely events for it to happen. | 0 to 10% or once every 25 yrs
Consequence | Rating | Criteria / Examples
Catastrophic | 5 | - Major problem from which there is no recovery. - Significant damage to organization credibility or integrity. - Complete loss of ability to deliver a critical program.
Major | 4 | - Event that requires a major realignment of how service is delivered. - Significant event which has a long recovery period. - Failure to deliver a major political commitment.
Moderate | 3 | - Recovery from the event requires cooperation across departments. - May generate media attention.
Minor | 2 | - Can be dealt with at a department level but requires Executive notification. - Delay in funding or change in funding criteria. - Stakeholder or client would take note.
Insignificant | 1 | - Can be dealt with internally at the business unit level. - No escalation of the issue required. - No media attention. - No or manageable stakeholder or client interest.
Risk Rating Matrix

## 5. Evaluation
RISK EVALUATION
In order to EVALUATE risks, the ADEQUACY OF CURRENT TREATMENTS (Column L) and ACTION (Column M) are determined ADEQUACY OF CURRENT TREATMENTS: Use the drop-down in Column L to identify the risk tolerance of the organization considering the current treatments. Choices include: - Non-existent: there are no current treatments identified in Column G (are not doing anything) - Inadequate: the current treatments (Column G) do not meet the organization's risk tolerance and need attention (are not doing enough) - Adequate: the current treatments (Column G) meet the organization's risk tolerance and no further action is required (are doing enough) - Robust: the current treatments (Column G) exceed the organization's risk tolerance (are doing too much) ACTION: Use the drop-down in Column M to identify the action the organization will take to respond to the risk, if any Choices incude: - Accept: no further action is required - Monitor: Accept and keep an eye on future trends that may impact the currently accepted risk tolerance - Treat: implement ADDITIONAL TREATMENTS to either reduce the likelihood (Column H) or reduce the impact if the risk event occurs (Column I) - Transfer: allocate the risk responsibility to another party through legal contract (e.g. hire another party and transfer the risk to them) - Avoid: do not pursue the objective to avoid the potential consequences identified that are outside of the risk tolerance of the organization TREND: Use the drop-down in Column N to identify the trend of the risk rating since the last reporting period (if applicable). Choices incude: - New Risk: the risk was not included in the last reporting period - Downward: the risk rating (Column J) has decreased since the last reporting period - Static: the risk rating (Column J) has not changed since the last reporting period - Upward: the risk rating (Column J) has increased since the last reporting period

## Sample
--SAMPLE -- XYZ Organization
This risk assessment is connected to/aligns with: |  |  | Enterprise wide operational risk register
Objective: |  |  | Directive by VP of IT Department
Date of the risk assessment: |  |  | <date>
Risk should be reassessed periodically throughout the life of the program or project.
Future date(s) to reassess the risks within the register: |  |  | <date>
RISK MANAGEMENT PROCESS (For Guidance, See Tab 2) |  | CONTEXT (For Guidance, See Tab 3) | RISK IDENTIFICATION |  |  |  | ANALYSIS Residual risk rating with treatments in place (For Guidance, See Tab 4) |  |  |  | EVALUATION (For Guidance, See Tab 5) |  |  | TREATMENT MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all mitigations Additional Mitigations are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of mitigations implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Maximum level of risk executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned mitigations, and associated costs)
RISK # | CATEGORY | BUSINESS OBJECTIVE/ PRIORITY | RISK EVENT | RISK CAUSE | IMPACT | CURRENT TREATMENTS | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | ADEQUACY OF CURRENT TREATMENTS | ACTION | TREND | ADDITIONAL PLANNED TREATMENT | DELIVERABLES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | STATUS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP
Add identifiers to better organize and track risks. | Which category does this Risk Event fall under? | What business objective/priority does this Risk Event affect (e.g., Mandate letter, strategic directive, etc.)? | What events could impact the achievement of objectives (can be positive or negative)? | What Risk Cause (trigger, circumstance, uncertainty) could increase the Likelihood of the Risk Event occurring? There are usually multiple Risk Causes leading to a Risk Event. | How would the Risk Event impact the achievement of the objective/priority? | What Treatments are currently in place to manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | How likely? | How severe? | (LxC) | Rating with current treatments in place | Non-existent Inadequate Adequate Robust | Will you do more to manage the risk (treat) or choose to accept and monitor? | If applicable, has this risk rating changed over time? Has column J increased (upward trend), decreased (downward trend) or not changed (static) | What Treatments are needed to further manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | Future Treatments will come in what form (e.g., a project plan, a briefing note, report, funding request, other)? | Who will take the lead on this mitigation? | When should the deliverable be ready? (Optional) | Do the Risk Event or Treatments depend on another team or organization? Do they impact another group? | On Track Slowed Stalled |  |  |  |  | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place
OFP 1 | Operational - Financial Processes | Timely service delivery to clients. | Invoice delivery to clients is slow and inaccurate. | - Legacy system is incompatible with data input requirements. - Data entry practices inconsistent - Manual data checks | - Unmet client service quality performance - Increased A/R - Increased risk of loss - Increased cost of recovery | - Manual data checks - Training manual | 3 | 4 | 12 | HIGH | Inadequate | Treat | Downward | Long term: - System replacement Short term: - Update training manual - Commit more staff time. | - System replacement strategy - Revised training manual and web counterpart - Staffing solution for short term | - Systems replacement: Tom - Training manual: Sarah - Staff review: Tom | - System replacement strategy: End of fiscal - Training manual: February 14th - Staffing review and recommendation: February 7th | System shared with IT Department. |  | 25% - Initial planning complete. Implementation expected once additional staff sourced. | Further progress is dependant upon staffing approval |  |  | 2 | 4 | 8 | MEDIUM | 3 | 4 | 12 | HIGH | 2 | 4 | 8 | MEDIUM
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED